## BBQ's and Parties
BBQ'S, Parties and Picnics |  |  |  |  | Event Contacts
Media Contact
Event Co-Ordinator | Key Team Members | Main Supporters/Community Groups |  |  | Logistics Contact
Megan Lamb 0421 192 822
Logistics Co-Ordinator |  |  |  |  | Sponsor Contact
Set Up Contact
Performance Co-Ordinator |  |  |  |  | Pack Down Contact
After Event Follow Up
3 month before: | 2 months before: | 1 month before: | Organise 1 week before: | BBQ Bag: | On the Day (Run Sheet) (or before if required)
Park | Equipment Hire & Purchases: | Follow Up: | General | Kids Games - General | Collect Food & Other Items (Meat, Bread, Napkins, Tomato Sauce)
Easy Access via Public Transport | PA System | Community Groups re Activities | Order Sausages (1kg = 10 sausage @ $4.99kg) | Soccer Balls | Collect Sausages
BBQ or Picnic | Stage | Stalls from Local Service Providers/Groups | Order Loaves of Bread (1 Loaf per 15 Sausages) | Cricket Set | Collect Bread
Public Toilets | Marquee | Meet with organisers |  | Hand Sanitiser | Collect Ice
Play Equipment | Portable Toilets (@250ea) | Media Opportunities/ Good News Stories | Check Organisation BBQ Bag & Order following if required: | Picnic Blanket | Purchase Other items as required (list supplied by Organisation Co-ordinator)
Insurance Requirements | Garbage Removal ($30ea) | Speeches/Acknowledgements/Acknowledge Country | Tomato Sauce | Bunting | Bring Water
Map | Book Venue | Mayor | Napkins | Balloons | Collect BBQ & Trestle Table & Picnic Blankets
Water Access |  | MP | Cordial | Shade | Collect Organisation BBQ Bag
Public BBQ's | Invite: | Community Representative | Water | Marketing Materials | Collect Gas Bottle
Access to Power | Mayor/s | Refugee/Migrant | First Aid | Donation Tin
| Council |  | BBQ | Table Cloth
Sports - UniSA | Local Members |  | Water | Bocce
Activities | Community Groups | Kids Games: | BBQ Cleaner | Totem Tennis | Event Run Sheet:
Kids Games | Service Providers | Large Noughts & Crosses | Tea Towels | Name Tags and Markers
Balloons |  | Large Jenga | BBQ Utensils | Volunteer Forms and Newsletter Sign Up Sheets
Kids Rides | Estimate Numbers of Attendance | Soccer | Metal Trays | Basket Ball | Volunteer Team to Arrive
| Set Date: | Cricket | Trestle Table | Sunscreen | Core Team arrive 1.5 hours early for set up (4-6 people)
Promotion & Marketing |  | Bocce | Newspaper |  | Other sponsors arrive (1 hour)
Promotion - Facebook | Book Entertainment, Kids fun! | Treasure Hunt | Toilet Paper |  | Other Volunteers arrive 0.5 hours before to help with final set up
Promotion - Facebook Event | Facepainter ($180 2 hours) | Pinata | Gas Bottle
Promotion - Newsletter | Bouncy Castle ($500-$800) | Musical Chairs | Table Cloth |  | Prior to Event
Promotion - Mail Out | Balloon Maker ($200) | Hop Scotch | Picnic Blankets
Promotion - Flyer | Entertainers ($300 hour) | Obstacle Course | Chairs |  | If required Organisation Co-ordinator arrive earlier for other services/deliveries
Promotion - Poster | Clown ($300 hour) |  | Cleaning Supplies |  | (with one other nominated Organisation person)
Promotion - Letter Box Drop | Roaming Performers ($300 hour) |  | Rubbish Bags
| Order Helium Balloons | #teamOrganisation | Hand Sanitiser
Council & Local Members & MP's |  | Secure Names on the Day | Cans of Drink |  | Arrive on Site - Core Team | 1.5 hours before event start
Notified Community Centres, Services, Schools and Sports | Music | Distribute Roles | Cooking Oil |  | Set up Food Serving Table (put out bread, sauce, napkins)
Funding/Grants/Sponsorship | PA System | Create Run Sheet | Gloves |  | Set up BBQ & Check Gas Bottle
Contact Council | Bands |  |  |  | Put Drinks in Tubs and then put ice in tubs
Contact Local Members | Performers |  | #teamOrganisation |  | Set up Picnic Blankets
| DJ |  | Confirm peoples availability |  | Set up PA Area & Stage
|  |  | Send Run sheet to key people |  | Open Toilets and Check Area
| Promotional Printing |  | Send contact details to key people |  | Check Garbage Bins
| Design Work |  |  |  | Set up Organisation Stand with Brochures, Donation Tins, Newsletter forms
Set up Lost & Found, First Aid and Information at Organisation Stand (Tubs)
| Flyers 1000 @ $100 |  |  |  | Put out signage on near roads
| You are Organisation Here Stickers |  |  |  | Set up Bunting, Balloons and other decorations near stage and Organisation Stand
| Posters 50 x A2 = $45 |  |  |  | Strategically place helium balloons
| Business Cards 1000 = $85 |  |  |  | Meet Activity People if required
| Magnets 500 @ $313 |  |  |  | Mark out Areas for Activities
| A Frame $194 ea |  |  |  | Set up Marquee or Umbrellas if required
Meet any catering people if required
[5 empty] | Kids Actitivies Team Arrive | 1 hour before
Set up Kids Games area
Set up Soccer
Get Cricket Read
[5 empty] | Other Service Providers/ Community Groups/Partners/ Musicians/Bands/Performers | 1 hour before
Arrive and Set up Tables or Areas
[5 empty] | Briefing all teams, service providers and key team members | 1/2 hour before
Plans for the day, Core Values, How to Organisation, Photo's, Media opportunities
Time for last minute Questions
Event Start
[5 empty] | Start BBQ Cooking & Serving of Food | Event Start
[5 empty] | Start Music - Someone to look after music | Event Start
[5 empty] | Organisationrs! 2 people at entry point to Organisation people for first half hour | Event Start - 1/2hr
[5 empty] | Encourage other Community Leaders to Organisation people and Circulate | Continuous
[5 empty] | Kids Activities team encourage interaction of children and families in activities | Continuous
[5 empty] | #team Organisation to Circulate crowd and offer Organisation encourage interaction | Continuous
[5 empty] | Organisation Stand - needs to be rotated every half hour with other #teamOrganisation people | Continuous
[5 empty] | Organisation Co-ordinator to check on Service Providers | 1 hour after start
[5 empty] | Team Member to Check toilet and bins | 1 hour after start
[5 empty] | Face Painter/Balloon Maker to arrive | 1/2hr after start
[5 empty] | Bands/Musicians/Entertainers | 1/2hr after start
[5 empty] | Speeches, Organisations, Acknowledgements | 1 hour after start
Acnowledge Country
Sponsors Speech (over $500)
Organisation Speech - Thank Sponsors, Organisationrs, About Organisation, Event Finish time. How to get involved
Other Speech (TBC) - Refugee or Multicultural
[5 empty] | Let activities run naturally, announce at different times activities starting on PA system: | After Speeches in succession
Treasure Hunt (Sponsored By over at….)
Egg & Spoon
Tug of War
Sack Race
Speech - Major Sponsor or Organisation. Thank everyone for coming. Promote next event
[5 empty] | Pack Down, Clean Up. | Event Finish Time
[5 empty] | Remove Rubbish From Site if Required | Event Finish Time
[5 empty] | Team Briefing Session | After Pack Down
Final Team wait for any final collections or deliveries